## Main page
Team Naboo KPIs
|  | Total est. time | Total actual time | Remaining task | Time admin | Time production
| sprint 2 | 66 | 13 | 5 | 20.7 | 13
| sprint 3 | 0 | 0 | 0 | 0 | 0
| sprint 4 | 0 | 0 | 0 | 0 | 0
| sprint 5 | 0 | 0 | 0 | 0 | 0
Estimated time vs acctual time spent, per task
(Should be as close to 1 as possible)
Remaining tasks after finished sprint
(Should be as close to 0 as possible)
Total time spent, admin vs production
(What do we spend most time on, meetings or coding)

## Sprint 2
Sprint 2 - 20/9 - 26/9
Estimated time vs acctual time spent, per task
| Task name/nr | Estimated time | Time spent Robert | Time spent Johan | Time spent Pierre | Time spent Sebastian | Time spent Oscar | Done? | Total time spent on tasks
| Create KPI / TN-21 | 8 | 4 | 3.5 |  |  |  | 1 | 7.5
| Create a basic database / TN-26 | 16 | [6 empty] | 0
| Database handler / TN-27 | 16 | [6 empty] | 0
| Create a design/UML pattern / TN-22 | 16 | 2 | [5 empty] | 2
| Investigate database API from Rambo AB / TN-24 | 2 | [6 empty] | 0
| Create screen with bin suggestion / TN-25 | 8 |  | 3.5 |  |  |  |  | 3.5
0
0
0
0
Total: | 6 | 66 | 6 | 7 | 0 | 0 | 0 | 1 | 13
Total time spent admin
| Day |  | Time spent Robert | Time spent Johan | Time spent Pierre | Time spent Sebastian | Time spent Oscar |  | Total time spent on admin
| Monday |  | 0.5 | 0.5 |  | 0.5 | 0.5 |  | 2
| Tuesday |  | 3.5 | 3.5 | 3.5 | 3.5 |  |  | 14
| Wednesday | [7 empty] | 0
| Thursday | [7 empty] | 0
| Friday |  |  | 0.7 |  |  |  |  | 0.7
| Saturday | [7 empty] | 0
| Sunday |  | 1 |  | 1 | 1 | 1 |  | 4
Total: |  |  | 5 | 4.7 | 4.5 | 5 | 1.5 |  | 20.7
| Remaining tasks | 5

## Sprint 3
Sprint 3 - 27/9 - 3/10
Estimated time vs acctual time spent, per task
| Task name/nr | Estimated time | Time spent Robert | Time spent Johan | Time spent Pierre | Time spent Sebastian | Time spent Oscar | Done? | Total time spent on tasks
Total: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total time spent admin
| Day |  | Time spent Robert | Time spent Johan | Time spent Pierre | Time spent Sebastian | Time spent Oscar |  | Total time spent on admin
| Monday | [7 empty] | 0
| Tuesday | [7 empty] | 0
| Wednesday | [7 empty] | 0
| Thursday | [7 empty] | 0
| Friday | [7 empty] | 0
| Saturday | [7 empty] | 0
| Sunday | [7 empty] | 0
Total: |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
| Remaining tasks | 0

## Sprint 4
Sprint 4 - 4/10 - 10/10
Estimated time vs acctual time spent, per task
| Task name/nr | Estimated time | Time spent Robert | Time spent Johan | Time spent Pierre | Time spent Sebastian | Time spent Oscar | Done? | Total time spent on tasks
0
0
0
0
0
0
0
0
0
0
Total: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total time spent admin
| Day |  | Time spent Robert | Time spent Johan | Time spent Pierre | Time spent Sebastian | Time spent Oscar |  | Total time spent on admin
| Monday | [7 empty] | 0
| Tuesday | [7 empty] | 0
| Wednesday | [7 empty] | 0
| Thursday | [7 empty] | 0
| Friday | [7 empty] | 0
| Saturday | [7 empty] | 0
| Sunday | [7 empty] | 0
Total: |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
| Remaining tasks | 0

## Sprint 5
Sprint 5 - 11/10 - 17/10
Estimated time vs acctual time spent, per task
| Task name/nr | Estimated time | Time spent Robert | Time spent Johan | Time spent Pierre | Time spent Sebastian | Time spent Oscar | Done? | Total time spent on tasks
0
0
0
0
0
0
0
0
0
0
Total: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total time spent admin
| Day |  | Time spent Robert | Time spent Johan | Time spent Pierre | Time spent Sebastian | Time spent Oscar |  | Total time spent on admin
| Monday | [7 empty] | 0
| Tuesday | [7 empty] | 0
| Wednesday | [7 empty] | 0
| Thursday | [7 empty] | 0
| Friday | [7 empty] | 0
| Saturday | [7 empty] | 0
| Sunday | [7 empty] | 0
Total: |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
| Remaining tasks | 0